## Procurement Plan WBDRBMP
Item: | Activity no. | Activity | Type | Proc. method | Pcks. | Post/Prior | Issue | Bids received | Ctr. Signed | Ctr Complete | Contract amount in USD | Disbursed amount in USD | Difference between cost estimate and contracted amount in % | NOTE
Component 1: Multi-state Cooperation on International Drina Management
Sub-component 1.A: Development of an agreed Strategic Action Program (SAP) mainstreaming transboundary IWRM and climate change adaptation in national planning
1 | 1.A.1 | Preparation of a Drina Basin Strategic Action Program (SAP) | CS | QCBS | 1 | Post | 2017-12-01 | 2018-04-01 | 2018-06-01 | 2019-12-01
2 | 1.A.2 | Hydraulic and Hydrologic Model for the Drina River Basin with Reservoir Operation Optimization | CS | QCBS | 1 | Post | 2017-09-01 | 2017-12-01 | 2018-02-01 | 2020-02-01
3 | 1.A.3. | Purchase of incremental equipment (automated flow /level gauges) and ICT software and hardware
4 | 1.A.3.2.1 | ICT - hardware, server | G | SH | 1 | Prior | 2017-09-01 | 2017-10-01 | 2017-10-10 | 2017-11-10
5 | 1.A.3.2.2 | ICT - software (licences, basic server software, 2 client applications + automation module). Installation and training at customer’s site. | G | DC | 1 | Post | 2017-09-01 | 2017-10-01 | 2017-10-10 | 2020-05-01
6 | 1.A.4 | Preparation of water resources and basin study | CS | QCBS | 1 | Prior | 2017-09-01 | 2017-12-01 | 2018-02-01 | 2020-02-01
7 | 1.A.5 | Preparation of Study for analyses of the pollution of DRB | CS | CQ | 1 | Post | 2017-12-01 | 2018-02-01 | 2018-03-01 | 2018-09-01
Sub-component 1.B: Institutional Development and Capacity Building
8 | 1.B.1 | Support to the DTF and stakeholders all coordination DRB activities | OC | SOE | multiple | NA | during the life of the project - till 2020
9 | 1.B.2 | Procurement of equipment | G | SH | 1 | Post | 2017-09-01 | 2017-10-01 | 2017-10-10 | 2017-11-10
10 | 1.B.3 | Support to preparation national and local policy and regulatory reforms to confirm to the international DRB management | CS | CQ | 1 | Post | 2017-11-01 | 2017-12-02 | 2018-01-03 | 2019-07-04
11 | 1.B.4 | Participation in GEF IW:LEARN activities | TR | SOE | multiple | NA | during the life of the project - till 2020
Component 2: Pilot investments for Integrated Basin Management and Climate Change Resilience
Sub-component 2.A : Strengthening capacity for climate change resilience.
12 | 2.A.1 | Strengthening the Hydrometeological Services by procuring equipment in BiH (FBiH and RS), Serbia and Montenegro
13 | 2.A.1.1 | LOT 1:Improving the existing meteorological and precipitation stations network | G | ICB | 4 | Prior | 2017-08-01 | 2017-09-15 | 2017-10-30 | 2018-04-10
14 | 2.A.1.2 | LOT 2: Providing conditions for the reliable rating curves at hydrological stations
15 | 2.A.1.3 | LOT 3: Rehabilitation, modernizing and completing hydrological stations facilities
16 | 2.A.1.4 | LOT 4: Procurement of Cableway
17 | 2.A.2 | Develop protocols to improve data compatibility among the three countries | TR | SOE | multiple | NA | during the life of the project - till 2020
18 | 2.A.3 | Public Awareness Program | CS | CQ | 1 | Post | during the life of the project - till 2020
19 | 2.A.4 | Small Grants Program | TR | NA | during the life of the project - till 2020
20 | 2.A.5 | Enhanced Flood Forecasting and Early Warning System at regional scale to complement the existing ones in the riparian countries
21 | 2.A.5.1 | Capacity building for implementation of flood and drought resilience measures - trainings, seminars and workshops | CS | CQ | 1 | Post | 2017-09-01 | 2017-11-02 | 2017-12-03 | 2019-10-04
Sub-component 2.B: Pilot Investments for Basin Climate Change Resilience and flood management
22 | 2.B.1 | Works/ infrastructure and equipment to pilot climate change resilience approaches and designs
23 | 2.B.1.2 | Republic of Serbia - pilot investments
24 | 2.B.1.2.1 | Conceptual design for flood protection of the Mačva plain, section Loznica- Badovinci | CS | CQ | 1 | Post | 2017-09-01 | 2017-10-02 | 2017-11-01 | 2018-06-04
25 | 2.B.1.2.2 | Upgrade of existing flood protection from river Lim in Šarampov in the municipality of Prijepolje | G | NCB | 1 | Post | 2017-12-01 | 2018-02-01 | 2018-04-01 | 2018-10-01
26 | 2.B.1.3 | Montenegro - pilot investments
27 | 2.B.1.3.1. | Preparation of the Terms of Reference (ToR) for CS: Assessment of climate change impacts on groundwater in Drina Basin and conceptual design for the Flood protection, regulation and irrigation of Lim river basin (with Grnčar river) with the aim of mitigating the impact of climate change and sustainable use of natural resources. | CS | CQ | 1 | Post | 2017-07-01 | 2017-07-10 | 2017-07-15 | 2017-08-15
28 | 2.B.1.3.2 | Assessment of climate change impacts on groundwater in Drina Basin in Montenegro and preparation of the conceptual design for the Flood protection, regulation and irrigation of Lim river basin (with Grnčar river) with the aim of mitigating the impact of climate change and sustainable use of natural resources. | CS | QCBS | 1 | Post | 2017-09-15 | 2017-10-10 | 2017-11-01 | 2018-11-01
29 | 2.B.1.4 | BiH / Republic of Srpska - pilot investements
30 | 2.B.1.4.1 | River training of degraded banks of the Drina riverbed and its tributaries in urban city areas
31 | 2.B.1.4.1.1 | Preparation of feasibility study with priority list | CS | CQ | 1 | Post | 2017-09-01 | 2017-10-02 | 2017-11-01 | 2018-04-01
32 | 2.B.1.4.1.2 | Preparation of geodetic, engineering-geological and geomechanical bases in 5 municipalities including technical documentation/main projects | CS | CQ | 1 | Post | 2017-09-01 | 2017-10-02 | 2017-11-01 | 2018-04-01
33 | 2.B.1.4.1.3 | River training of riverbeds of watercourses Zidinski Potok and Surduk - Novo Gorazde | W | NCB | 1 | Post | 2017-09-01 | 2017-10-02 | 2017-11-01 | 2018-04-01
34 | 2.B.1.4.1.4 | Recovery of landslide at 14 localities in Bratunac municipality | W | NCB | 1 | Post | 2017-09-01 | 2017-10-02 | 2017-11-01 | 2018-04-01
35 | 2.B.1.4.2 | Protection against high waters and the arrangement of the lovnica river riverbed in the area of monastery complex Lovnica | W | NCB | 1 | Post | 2017-09-01 | 2017-10-02 | 2017-11-01 | 2018-04-01
36 | 2.B.1.4.3 | Preparation of feasibility study for identification of leachate at the area of the City of Bijeljina and upgrade of leachate treatment system at Regional sanitary landfill „Brijesnica“
37 | 2.B.1.4.3.1 | Preparation of feasibility study | CS | CQ | 1 | Post | 2017-09-01 | 2017-10-01 | 2017-11-01 | 2018-01-03
38 | 2.B.1.4.3.2 | Upgrade of leachate treatment system at Regional sanitary landfill „Brijesnica“ | W | NCB | 1 | Post | 2017-10-01 | 2017-11-01 | 2017-12-01 | 2018-06-01
39 | 2.B.1.5 | BiH / Federation BiH - pilot investements
40 | 2.B.1.5.1 | Feasibility study and preliminary design for waste water collector and treatment plant for Bosansko-Podrinjski Kanton | CS | QCBS | 1 | Post | 2017-09-01 | 2018-01-03 | 2018-03-03 | 2019-03-03
Component 3: Project management, Monitoring and Evaluation
41 | 3.1 | PMT costs (in BiH together with FBiH costs) | OC | SOE | multiple | NA | during the life of the project - till 2020
42 | 3.2 | APCU costs (in BiH/Republika Srpska) | OC | SOE | multiple | NA | during the life of the project - till 2020
43 | 3.3 | PIT costs ( in MNE ) | OC | SOE | multiple | NA | during the life of the project - till 2020
44 | 3.4 | PIU costs (in Republic of SERBIA) | OC | SOE | multiple | NA | during the life of the project - till 2020

## Thresholds
Thresholds for Procurement Methods and Bank Prior Review
Procurement Method | USD equivalent | Comments
Goods / Works |  | Thresholds for prior review:
International Competitive Bidding (ICB) Goods | > 1,000,000 | Works above 15 US$ Million per contract Goods above 4 US$ Million per contract All NCB tenders are subject to post review
International Competitive Bidding (ICB) Works | < 5,000,000
National Competitive Bidding (NCB) Goods | < 1,000,000
National Competitive Bidding (NCB) Works | < 5,000,000
Shopping (Goods) | < 100,000
Shopping (Works) | < 200,000
Direct Contracting (DC) | -
Consultancy Services |  | Thresholds for prior review:
Quality and Cost Based Selection (QCBS) | > 300,000 | Firms consultant Services above 2 US$ Million per contract Individuals above 0.4 US$ Million per contract All CQS are subject to post review
Quality Based Selection (QBS), Fixed Budget Selection (FBS), and Least Cost Selection (LCS) | -
Selection Based on Consultants’ Qualifications (CQS) | < 300,000
Single-Source Selection (SSS) | -